## Hoja1
RECEPCION DE MATERIALES PROYECTO EL JOBO
ITEM | DESCRIPCION | Ø | UND | QTY | OC | N° REMISION | PROVEEDOR | FECHA | COMENTARIOS
| BLEED RING 8"X 3/4" THRD CLASS 600 A105 RF | 8"X3/4" | und. | 2 | 110 | RMC-1509588 | JD VALVULAS | 2015-09-11
| CAP 2" - SHC/80, ASTM A 234WPB | 2" | und. | 2 | 209 | 10360 | TUVAPOR LTDA | 2015-10-15
| CAP SW 1" - 6000Lb ASTM A 105 ASME B16.11 | 1" | und. | 1 | 90 | RMC-1508582 | JD VALVULAS | 2015-08-27
| CAP SW 1" - 6000Lb ASTM A 105 ASME B16.11 | 1" | und. | 1 | 110 | RMC-1509588 | JD VALVULAS | 2015-09-11
| CAP SW 3/4" - 6000Lb ASTM A 105 ASME B16.11 | 3/4" | und. | 1 | 108 | S-001-00000010163 | TUVAPOR LTDA | 2015-09-02
| CAP SW 3/4" - 6000Lb ASTM A 105 ASME B16.11 | 3/4" | und. | 1 | 108 | S-001-00000010163 | TUVAPOR LTDA | 2015-09-02
| CAP THRD 1 1/2" - 6000Lb ASTM A 105 ASME B 16.11 | 1 1/2" | und. | 4 | 108 | S-001-00000010163 | TUVAPOR LTDA | 2015-09-02
| COUPLING 1 1/2" THRD 6000 A105N | 1 1/2" | und. | 5 | 30 | RMC-1508563 | JD VALVULAS | 2015-08-06
| COUPLING 1" THR 3000Lb A105N GALVANIZED | 1" | und. | 4 | 108 | S-001-00000010172 | TUVAPOR LTDA | 2015-09-02
| COUPLING 1" THR 3000Lb A105N GALVANIZED | 1" | und. | 7 | 209 | 10366 | TUVAPOR LTDA | 2015-10-16
| COUPLING 1" THRD 3000 A105N | 1" | und. | 5 | 31 | 5112004740 | CASAVAL S.A | 2015-08-06
| COUPLING 1" THRD 6000 A105N | 1" | und. | 1 | 108 | S-001-00000010163 | TUVAPOR LTDA | 2015-09-02
| ELL45 1 THR 3000Lb ASTM A 105 | 1" | und. | 1 | 209 | 10360 | TUVAPOR LTDA | 2015-10-15
| ELL45 1 THR 3000Lb ASTM A 105 | 1" | und. | 4 | 209 | 10361 | TUVAPOR LTDA | 2015-10-15
| ELL45 LR S/80,CS,A-234 GR WPB,ASME B16.9, ASME B16.25. | 2" | und. | 7 | 30 | RMC-1508563 | JD VALVULAS | 2015-08-06
| ELL45 LR S/80,CS,A-234 GR WPB,ASME B16.9, ASME B16.25. | 10" | und. | 1 | 110 | RMC-1509588 | JD VALVULAS | 2015-09-11
| ELL45 LR S/80,CS,A-234 GR WPB,ASME B16.9, ASME B16.25. | 2" | und. | 2 | 110 | RMC-1509588 | JD VALVULAS | 2015-09-11
| ELL45 LR S/80,CS,A-234 GR WPB,ASME B16.9, ASME B16.25. | 8" | und. | 25 | 110 | RMC-1509588 | JD VALVULAS | 2015-09-11
| ELL45 LR S/80,CS,A-234 GR WPB,ASME B16.9, ASME B16.25. | 8" | und. | 2 | 30 | RMC-1508563 | JD VALVULAS | 2015-08-06
| ELL45 LR S/80,CS,A-234 GR WPB,ASME B16.9, ASME B16.25. | 10" | und. | 4 | 168 | RMC-1509603 | JD VALVULAS | 2015-09-18
| ELL45 LR S/80,CS,A-234 GR WPB,ASME B16.9, ASME B16.25. | 2" | und. | 5 | 168 | RMC-150904 | JD VALVULAS | 2015-09-21
| ELL45 LR S/STD,CS,A-234 GR WPB,ASME B16.9, ASME B16.25. | 6" | und. | 9 | 135 | RMC-1509594 | JD VALVULAS | 2015-09-10
| ELL45 LR S/STD,CS,A-234 GR WPB,ASME B16.9, ASME B16.25. | 6" | und. | 3 | 30 | FALTA REMISION | JD VALVULAS
| ELL45 LR S/STD,CS,A-234 GR WPB,ASME B16.9, ASME B16.25. | 8" | und. | 4 | 168 | RMC-1509603 | JD VALVULAS | 2015-09-18
| ELL45 LR S/STD,CS,A-234 GR WPB,ASME B16.9, ASME B16.25. | 16" | und. | 1 | 168 | RMC-150904 | JD VALVULAS | 2015-09-21
| ELL45 LR S/STD,CS,A-234 GR WPB,ASME B16.9, ASME B16.25. | 3" | und. | 2 | 272 | 10433 | TUVAPOR LTDA | 2015-10-30
| ELL90 1 1/2" SW 3000Lb ASTM A 105 | 1 1/2" | und. | 6 | 30 | FALTA REMISION | JD VALVULAS
| ELL90 1 1/2" THR 3000Lb ASTM A 105 | 1 1/2" | und. | 1 | 31 | 5112004740 | CASAVAL S.A | 2015-08-06
| ELL90 1 SW 3000Lb ASTM A 105 | 1" | und. | 19 | 209 | 10360 | TUVAPOR LTDA | 2015-10-15
| ELL90 1 SW 3000Lb ASTM A 105 | 1" | und. | 1 | 214 | 1510625 | JD VALVULAS | 2015-10-16
| ELL90 1 SW 6000Lb ASTM A 105 | 1" | und. | 1 | 208 | RMC-1510622 | JD VALVULAS | 2015-10-13
| ELL90 1 SW 6000Lb ASTM A 105 | 1" | und. | 1 | 201 | RMC-1509614 | JD VALVULAS | 2015-09-30
| ELL90 1 THR 3000Lb ASTM A 105 | 1" | und. | 6 | 30 | RMC-1508563 | JD VALVULAS | 2015-08-06
| ELL90 1 THR 3000Lb ASTM A 105 | 1" | und. | 12 | 108 | S-001-00000010163 | TUVAPOR LTDA | 2015-09-02
| ELL90 1 THR 3000Lb ASTM A 105 | 1" | und. | 22 | 209 | 10360 | TUVAPOR LTDA | 2015-10-15
| ELL90 1 THR 3000Lb ASTM A 105 GALVANIZED | 1" | und. | 10 | 108 | S-001-00000010163 | TUVAPOR LTDA | 2015-09-02
| ELL90 1 THR 6000Lb ASTM A 105 | 1" | und. | 12 | 108 | S-001-00000010163 | TUVAPOR LTDA | 2015-09-02
| ELL90 1 THR 6000Lb ASTM A 105 | 1" | und. | 10 | 209 | 10360 | TUVAPOR LTDA | 2015-10-15
| ELL90 3/4" SW 6000Lb ASTM A 105 | 3/4" | und. | 1 | 214 | 1510625 | JD VALVULAS | 2015-10-16
| ELL90 LR S/160,CS,A-234 GR WPB,ASME B16.9, ASME B16.25. | 2" | und. | 8 | 110 | RMC-1509588 | JD VALVULAS | 2015-09-11
| ELL90 LR S/160,CS,A-234 GR WPB,ASME B16.9, ASME B16.25. | 2" | und. | 3 | 30 | FALTA REMISION | JD VALVULAS
| ELL90 LR S/80,CS,A-234 GR WPB,ASME B16.9, ASME B16.25. | 10" | und. | 3 | 110 | RMC-1509588 | JD VALVULAS | 2015-09-11
| ELL90 LR S/80,CS,A-234 GR WPB,ASME B16.9, ASME B16.25. | 2" | und. | 29 | 110 | RMC-1509588 | JD VALVULAS | 2015-09-11
| ELL90 LR S/80,CS,A-234 GR WPB,ASME B16.9, ASME B16.25. | 6" | und. | 9 | 132 | RMC-15091596 | JD VALVULAS | 2015-09-10
| ELL90 LR S/80,CS,A-234 GR WPB,ASME B16.9, ASME B16.25. | 6" | und. | 2 | 110 | RMC-1509588 | JD VALVULAS | 2015-09-11
| ELL90 LR S/80,CS,A-234 GR WPB,ASME B16.9, ASME B16.25. | 2" | und. | 41 | 30 | RMC-1508563 | JD VALVULAS | 2015-08-06
| ELL90 LR S/80,CS,A-234 GR WPB,ASME B16.9, ASME B16.25. | 8" | und. | 17 | 110 | RMC-1509588 | JD VALVULAS | 2015-09-11
| ELL90 LR S/80,CS,A-234 GR WPB,ASME B16.9, ASME B16.25. | 6" | und. | 10 | 30 | RMC-1508563 | JD VALVULAS | 2015-08-06
| ELL90 LR S/80,CS,A-234 GR WPB,ASME B16.9, ASME B16.25. | 8" | und. | 39 | 30 | RMC-1508563 | JD VALVULAS | 2015-08-06
| ELL90 LR S/80,CS,A-234 GR WPB,ASME B16.9, ASME B16.25. | 10" | und. | 5 | 168 | RMC-1509603 | JD VALVULAS | 2015-09-18
| ELL90 LR S/80,CS,A-234 GR WPB,ASME B16.9, ASME B16.25. | 8" | und. | 8 | 168 | RMC-150904 | JD VALVULAS | 2015-09-21
| ELL90 LR S/80,CS,A-234 GR WPB,ASME B16.9, ASME B16.25. | 2" | und. | 57 | 168 | RMC-150904 | JD VALVULAS | 2015-09-21
| ELL90 LR S/80,CS,A-234 GR WPB,ASME B16.9, ASME B16.25. | 8" | und. | 1 | 204 |  | JD VALVULAS
| ELL90 LR S/80,CS,A-234 GR WPB,ASME B16.9, ASME B16.25. | 2" | und. | 8 | 214 | 1510625 | JD VALVULAS | 2015-10-16
| ELL90 LR S/80,CS,A-234 GR WPB,ASME B16.9, ASME B16.25.. | 10" | und. | 4 | 30 | RMC-1508563 | JD VALVULAS | 2015-08-06
| ELL90 LR S/STD,CS,A-234 GR WPB,ASME B16.9, ASME B16.25. | 8" | und. | 15 | 208 | RMC-1510623 | JD VALVULAS | 2015-10-14
| ELL90 LR S/STD,CS,A-234 GR WPB,ASME B16.9, ASME B16.25. | 16" | und. | 4 | 110 | RMC-1509588 | JD VALVULAS | 2015-09-11
| ELL90 LR S/STD,CS,A-234 GR WPB,ASME B16.9, ASME B16.25. | 4" | und. | 8 | 110 | RMC-1509588 | JD VALVULAS | 2015-09-11
| ELL90 LR S/STD,CS,A-234 GR WPB,ASME B16.9, ASME B16.25. | 16" | und. | 9 | 30 | RMC-1508563 | JD VALVULAS | 2015-08-06
| ELL90 LR S/STD,CS,A-234 GR WPB,ASME B16.9, ASME B16.25. | 6" | und. | 6 | 30 | RMC-1508563 | JD VALVULAS | 2015-08-06
| ELL90 LR S/STD,CS,A-234 GR WPB,ASME B16.9, ASME B16.25. | 6" | und. | 9 | 156 | S-001-00000010251 | TUVAPOR LTDA | 2015-09-17
| ELL90 LR S/STD,CS,A-234 GR WPB,ASME B16.9, ASME B16.25. | 6" | und. | 4 | 168 | RMC-1509603 | JD VALVULAS | 2015-09-18
| ELL90 LR S/STD,CS,A-234 GR WPB,ASME B16.9, ASME B16.25. | 8" | und. | 11 | 168 | RMC-1509603 | JD VALVULAS | 2015-09-18
| ELL90 LR S/STD,CS,A-234 GR WPB,ASME B16.9, ASME B16.25. | 8" | und. | 1 | 209 | 10360 | TUVAPOR LTDA | 2015-10-15
| ELL90 LR S/STD,CS,A-234 GR WPB,ASME B16.9, ASME B16.25. | 3" | und. | 14 | 272 | 10433 | TUVAPOR LTDA | 2015-10-30
| FLANGE 1 1/2" THRD 600 RF A 105 | 1 1/2" | und. | 1 | 30 | RMC-1508563 | JD VALVULAS | 2015-08-06
| FLG, RF BLIND 150LB, CS,ASTM A-105, ASME B16.5. | 16" | und. | 2 | 91 | RMC-1508583 | JD VALVULAS | 2015-08-27
| FLG, RF BLIND 150LB, CS,ASTM A-105, ASME B16.5. | 16" | und. | 1 | 110 | RMC-1509588 | JD VALVULAS | 2015-09-11
| FLG, RF BLIND 150LB, CS,ASTM A-105, ASME B16.5. | 2" | und. | 7 | 108 | S-001-00000010163 | TUVAPOR LTDA | 2015-09-02
| FLG, RF BLIND 150LB, CS,ASTM A-105, ASME B16.5. | 4" | und. | 2 | 168 | RMC-1509603 | JD VALVULAS | 2015-09-18
| FLG, RF BLIND 150LB, CS,ASTM A-105, ASME B16.5. | 3" | und. | 1 | 272 | 10433 | TUVAPOR LTDA | 2015-10-30
| FLG, RF BLIND 600LB, ,CS,ASTM A-105, ASME B16.5. | 10" | und. | 1 | 108 | S-001-00000010163 | TUVAPOR LTDA | 2015-09-02
| FLG, RF BLIND 600LB, ,CS,ASTM A-105, ASME B16.5. | 10" | und. | 1 | 108 | S-001-00000010176 | TUVAPOR LTDA | 2015-09-03
| FLG, RF BLIND 600LB, ,CS,ASTM A-105, ASME B16.5. | 10" | und. | 1 | 31 | 5112004740 | CASAVAL S.A | 2015-08-06
| FLG, RF BLIND 600LB, ,CS,ASTM A-105, ASME B16.5. | 10" | und. | 2 | 87 | RMC-1508580 | JD VALVULAS | 2015-08-26
| FLG, RF BLIND 600LB, ,CS,ASTM A-105, ASME B16.5. | 2" | und. | 2 | 30 | RMC-1508563 | JD VALVULAS | 2015-08-06
| FLG, RF BLIND 600LB, ,CS,ASTM A-105, ASME B16.5. | 4" | und. | 2 | 9O | RMC-1508582 | JD VALVULAS | 2015-08-27
| FLG, RF BLIND 600LB, ,CS,ASTM A-105, ASME B16.5. | 6" | und. | 1 | 81 | RMC-1508579 | JD VALVULAS | 2015-08-26
| FLG, RF BLIND 600LB, ,CS,ASTM A-105, ASME B16.5. | 6" | und. | 1 | 30 | RMC-1508563 | JD VALVULAS | 2015-08-06
| FLG, RF BLIND 600LB, ,CS,ASTM A-105, ASME B16.5. | 8" | und. | 2 | 52 | 5112004774 | CASAVAL S.A | 2015-08-20
| FLG, RF BLIND 600LB, ,CS,ASTM A-105, ASME B16.5. | 10" | und. | 2 | 127 | FALTA REMISION | JD VALVULAS
| FLG, RF BLIND 600LB, ,CS,ASTM A-105, ASME B16.5. | 2" | und. | 2 | 127 | FALTA REMISION | JD VALVULAS
| FLG, RF BLIND 600LB, ,CS,ASTM A-105, ASME B16.5. | 4" | und. | 1 | 127 | FALTA REMISION | JD VALVULAS
| FLG, RF BLIND 600LB, ,CS,ASTM A-105, ASME B16.5. | 8" | und. | 7 | 31 | 5112004740 | CASAVAL S.A | 2015-08-06
| FLG, RF BLIND 600LB, ,CS,ASTM A-105, ASME B16.5. | 8" | und. | 3 | 127 | FALTA REMISION | JD VALVULAS
| FLG, RFWN 150B S/STD BORE,CS,ASTM A-105, ASME B16.5. | 16" | und. | 11 | 31 | 5112004740 | CASAVAL S.A | 2015-08-06
| FLG, RFWN 150B S/STD BORE,CS,ASTM A-105, ASME B16.5. | 16" | und. | 1 | 168 | RMC-1509603 | JD VALVULAS | 2015-09-18
| FLG, RFWN 150B S/STD BORE,CS,ASTM A-105, ASME B16.5. | 4" | und. | 1 | 168 | RMC-1509603 | JD VALVULAS | 2015-09-18
| FLG, RFWN 150B S/STD BORE,CS,ASTM A-105, ASME B16.5. | 16" | und. | 1 | 209 | 10360 | TUVAPOR LTDA | 2015-10-15
| FLG, RFWN 150B S/STD BORE,CS,ASTM A-105, ASME B16.5. | 14" | und. | 1 | 209 | 10360 | TUVAPOR LTDA | 2015-10-15
| FLG, RFWN 150LB S/80 BORE,CS,ASTM A-105,ASME B16.5. | 2" | und. | 35 | 31 | 5112004740 | CASAVAL S.A | 2015-08-06
| FLG, RFWN 150LB S/80 BORE,CS,ASTM A-105,ASME B16.5. | 2" | und. | 12 | 108 | S-001-00000010163 | TUVAPOR LTDA | 2015-09-02
| FLG, RFWN 150LB S/80 BORE,CS,ASTM A-105,ASME B16.5. | 2" | und. | 3 | 209 | 10360 | TUVAPOR LTDA | 2015-10-15
| FLG, RFWN 150LB S/STD BORE, ASTM A-105, ASME B16.5. | 8" | und. | 10 | 208 | RMC-1510623 | JD VALVULAS | 2015-10-14
| FLG, RFWN 150LB S/STD BORE, ASTM A-105, ASME B16.5. | 4" | und. | 10 | 108 | S-001-00000010163 | TUVAPOR LTDA | 2015-09-02
| FLG, RFWN 150LB S/STD BORE, ASTM A-105, ASME B16.5. | 6" | und. | 3 | 108 | S-001-00000010163 | TUVAPOR LTDA | 2015-09-02
| FLG, RFWN 150LB S/STD BORE, ASTM A-105, ASME B16.5. | 6" | und. | 9 | 31 | 5112004740 | CASAVAL S.A | 2015-08-06
| FLG, RFWN 150LB S/STD BORE, ASTM A-105, ASME B16.5. | 6" | und. | 8 | 135 | 5114019101 | CASAVAL S.A | 2015-08-06
| FLG, RFWN 150LB S/STD BORE, ASTM A-105, ASME B16.5. | 6" | und. | 8 | 156 | S-001-00000010251 | TUVAPOR LTDA | 2015-09-17
| FLG, RFWN 150LB S/STD BORE, ASTM A-105, ASME B16.5. | 8" | und. | 6 | 137 | FALTA REMISION | JD VALVULAS | 2015-09-11
| FLG, RFWN 150LB S/STD BORE, ASTM A-105, ASME B16.5. | 8" | und. | 18 | 167 | S-001-0000010257 | TUVAPOR LTDA | 2015-09-18
| FLG, RFWN 150LB S/STD BORE, ASTM A-105, ASME B16.5. | 3" | und. | 7 | 272 | 10433 | TUVAPOR LTDA | 2015-10-30
| FLG, RFWN 600LB S/80 BORE,CS,ASTM A-105, ASME B16.5. | 4" | und. | 3 | 84 | 5114019345 | CASAVAL S.A | 2015-08-27
| FLG, RFWN 600LB S/80 BORE,CS,ASTM A-105, ASME B16.5. | 4" | und. | 1 | 90 | RMC-1508582 | JD VALVULAS | 2015-08-27
| FLG, RFWN 600LB, S/160, BORE, ASTM A-105, ASME B16.5. | 12" | und. | 2 | 35 | 5303 | ACCEPETROL | 2015-08-10
| FLG, RFWN 600LB, S/80, BORE, ASTM A-105, ASME B16.5. | 2" | und. | 4 | 53 | RMC-1508572 | JD VALVULAS | 2015-08-18
| FLG, RFWN 600LB, S/80, BORE, ASTM A-105, ASME B16.5. | 6" | und. | 10 | 31 | 5112004740 | CASAVAL S.A | 2015-08-06
| FLG, RFWN 600LB, S/80, BORE, ASTM A-105, ASME B16.5. | 6" | und. | 3 | 84 | 5112004802 | CASAVAL S.A | 2015-08-27
| FLG, RFWN 600LB, S/80, BORE, ASTM A-105, ASME B16.5. | 2" | und. | 20 | 110 | RMC-1509588 | JD VALVULAS | 2015-09-11
| FLG, RFWN 600LB, S/80, BORE, ASTM A-105, ASME B16.5. | 3" | und. | 3 | 90 | RMC-1508582 | JD VALVULAS | 2015-08-27
| FLG, RFWN 600LB, S/80, BORE, ASTM A-105, ASME B16.5. | 10" | und. | 8 | 108 | S-001-00000010171 | TUVAPOR LTDA | 2015-09-02
| FLG, RFWN 600LB, S/80, BORE, ASTM A-105, ASME B16.5. | 10" | und. | 3 | 108 | S-001-00000010188 | TUVAPOR LTDA | 2015-09-07
| FLG, RFWN 600LB, S/80, BORE, ASTM A-105, ASME B16.5. | 10" | und. | 8 | 108 | S-001-00000010171 | TUVAPOR LTDA | 2015-09-02
| FLG, RFWN 600LB, S/80, BORE, ASTM A-105, ASME B16.5. | 8" | und. | 23 | 108 | S-001-00000010171 | TUVAPOR LTDA | 2015-09-02
| FLG, RFWN 600LB, S/80, BORE, ASTM A-105, ASME B16.5. | 8" | und. | 30 | 31 | 5112004740 | CASAVAL S.A | 2015-08-06
| FLG, RFWN 600LB, S/80, BORE, ASTM A-105, ASME B16.5. | 8" | und. | 6 | 53 | RMC-1508572 | JD VALVULAS | 2015-08-18
| FLG, RFWN 600LB, S/80, BORE, ASTM A-105, ASME B16.5. | 8" | und. | 1 | 81 | RMC-1508579 | JD VALVULAS | 2015-08-26
| FLG, RFWN 600LB, S/80, BORE, ASTM A-105, ASME B16.5. | 10" | und. | 12 | 31 | 5112004740 | CASAVAL S.A | 2015-08-06
| FLG, RFWN 600LB, S/80, BORE, ASTM A-105, ASME B16.5. | 10" | und. | 16 | 87 | RMC-1508580 | JD VALVULAS | 2015-08-26
| FLG, RFWN 600LB, S/80, BORE, ASTM A-105, ASME B16.5. | 2" | und. | 12 | 137 | FALTA REMISION | JD VALVULAS | 2015-09-11
| FLG, RFWN 600LB, S/80, BORE, ASTM A-105, ASME B16.5. | 6" | und. | 7 | 108 | S-001-00000010163 | TUVAPOR LTDA | 2015-09-02
| FLG, RFWN 600LB, S/80, BORE, ASTM A-105, ASME B16.5. | 6" | und. | 14 | 132 | RMC-15091596 | JD VALVULAS | 2015-09-10
| FLG, RFWN 600LB, S/80, BORE, ASTM A-105, ASME B16.5. | 2" | und. | 22 | 30 | RMC-1508563 | JD VALVULAS | 2015-08-06
| FLG, RFWN 600LB, S/80, BORE, ASTM A-105, ASME B16.5. | 8" | und. | 1 | 108 | S-001-00000010163 | TUVAPOR LTDA | 2015-09-02
| FLG, RFWN 600LB, S/80, BORE, ASTM A-105, ASME B16.5. | 2" | und. | 31 | 168 | RMC-1509603 | JD VALVULAS | 2015-09-18
| FLG, RFWN 600LB, S/80, BORE, ASTM A-105, ASME B16.5. | 8" | und. | 23 | 30 | RMC-1508563 | JD VALVULAS | 2015-08-06
| FLG, RFWN 600LB, S/80, BORE, ASTM A-105, ASME B16.5. | 10" | und. | 14 | 195 | RMC-1509612 | JD VALVULAS | 2015-09-29
| FLG, RFWN 600LB, S/80, BORE, ASTM A-105, ASME B16.5. | 10" | und. | 7 | 195 | RMC-1509612 | JD VALVULAS | 2015-09-30
| FLG, RFWN 600LB, S/80, BORE, ASTM A-105, ASME B16.5. | 6" | und. | 2 | 201 | RMC-1509614 | JD VALVULAS | 2015-09-30
| FLG, RFWN 600LB, S/80, BORE, ASTM A-105, ASME B16.5. | 8" | und. | 2 | 201 | RMC-1509614 | JD VALVULAS | 2015-09-30
| FLG, RFWN 600LB, S/80, BORE, ASTM A-105, ASME B16.5. | 10" | und. | 1 | 214 | 1510625 | JD VALVULAS | 2015-10-16
| FLG, RFWN 600LB, S/80, BORE, ASTM A-105, ASME B16.5. | 8" | und. | 2 | 214 | 1510625 | JD VALVULAS | 2015-10-16
| FLG, RFWN 600LB, S/80, BORE, ASTM A-105, ASME B16.5. | 6" | und. | 2 | 209 | 10366 | TUVAPOR LTDA | 2015-10-16
| FLG,SO 6OOLB, ASTM A-105, ASME B16.5. | 8" | und. | 1 | 31 | 5112004740 | CASAVAL S.A | 2015-08-06
| GASKET, SPIRAL WOUND , 1/8" THK, ANSI 150 AISI RF FLANGES, 304 SS WINDING MATERIAL, WITH STANDART NON ASBESTOS NON METALLIC FILLER AND CARBON STEEL GUIDE RING, MATERIAL PER API STD 601 | 2" | und. | 24 | 30 | FALTA REMISION | JD VALVULAS
| GASKET, SPIRAL WOUND , 1/8" THK, ANSI 150 AISI RF FLANGES, 304 SS WINDING MATERIAL, WITH STANDART NON ASBESTOS NON METALLIC FILLER AND CARBON STEEL GUIDE RING, MATERIAL PER API STD 601 | 2" | und. | 6 | 91 | RMC-1508583 | JD VALVULAS | 2015-08-27
| GASKET, SPIRAL WOUND , 1/8" THK, ANSI 150 AISI RF FLANGES, 304 SS WINDING MATERIAL, WITH STANDART NON ASBESTOS NON METALLIC FILLER AND CARBON STEEL GUIDE RING, MATERIAL PER API STD 601 | 16" | und. | 3 | 31 | 5112004740 | CASAVAL S.A | 2015-08-06
| GASKET, SPIRAL WOUND , 1/8" THK, ANSI 150 AISI RF FLANGES, 304 SS WINDING MATERIAL, WITH STANDART NON ASBESTOS NON METALLIC FILLER AND CARBON STEEL GUIDE RING, MATERIAL PER API STD 601 | 16" | und. | 3 | 31 | 5114019154 | CASAVAL S.A | 2015-08-13
| GASKET, SPIRAL WOUND , 1/8" THK, ANSI 150 AISI RF FLANGES, 304 SS WINDING MATERIAL, WITH STANDART NON ASBESTOS NON METALLIC FILLER AND CARBON STEEL GUIDE RING, MATERIAL PER API STD 601 | 2" | und. | 6 | 110 | RMC-1509588 | JD VALVULAS | 2015-09-11
| GASKET, SPIRAL WOUND , 1/8" THK, ANSI 150 AISI RF FLANGES, 304 SS WINDING MATERIAL, WITH STANDART NON ASBESTOS NON METALLIC FILLER AND CARBON STEEL GUIDE RING, MATERIAL PER API STD 601 | 6" | und. | 1 | 91 | RMC-1508583 | JD VALVULAS | 2015-08-27
| GASKET, SPIRAL WOUND , 1/8" THK, ANSI 150 AISI RF FLANGES, 304 SS WINDING MATERIAL, WITH STANDART NON ASBESTOS NON METALLIC FILLER AND CARBON STEEL GUIDE RING, MATERIAL PER API STD 601 | 6" | und. | 6 | 31 | 5112004740 | CASAVAL S.A | 2015-08-06
| GASKET, SPIRAL WOUND , 1/8" THK, ANSI 150 AISI RF FLANGES, 304 SS WINDING MATERIAL, WITH STANDART NON ASBESTOS NON METALLIC FILLER AND CARBON STEEL GUIDE RING, MATERIAL PER API STD 601 | 6" | und. | 8 | 135 | 5114019101 | CASAVAL S.A | 2015-08-06
| GASKET, SPIRAL WOUND , 1/8" THK, ANSI 150 AISI RF FLANGES, 304 SS WINDING MATERIAL, WITH STANDART NON ASBESTOS NON METALLIC FILLER AND CARBON STEEL GUIDE RING, MATERIAL PER API STD 601 | 6" | und. | 3 | 108 | S-001-00000010163 | TUVAPOR LTDA | 2015-09-02
| GASKET, SPIRAL WOUND , 1/8" THK, ANSI 150 AISI RF FLANGES, 304 SS WINDING MATERIAL, WITH STANDART NON ASBESTOS NON METALLIC FILLER AND CARBON STEEL GUIDE RING, MATERIAL PER API STD 601 | 2" | und. | 5 | 168 | RMC-1509603 | JD VALVULAS | 2015-09-18
| GASKET, SPIRAL WOUND , 1/8" THK, ANSI 150 AISI RF FLANGES, 304 SS WINDING MATERIAL, WITH STANDART NON ASBESTOS NON METALLIC FILLER AND CARBON STEEL GUIDE RING, MATERIAL PER API STD 601 | 4" | und. | 6 | 168 | RMC-1509603 | JD VALVULAS | 2015-09-18
| GASKET, SPIRAL WOUND , 1/8" THK, ANSI 150 AISI RF FLANGES, 304 SS WINDING MATERIAL, WITH STANDART NON ASBESTOS NON METALLIC FILLER AND CARBON STEEL GUIDE RING, MATERIAL PER API STD 601 | 8" | und. | 19 | 167 | S-001-0000010257 | TUVAPOR LTDA | 2015-09-18
| GASKET, SPIRAL WOUND , 1/8" THK, ANSI 150 AISI RF FLANGES, 304 SS WINDING MATERIAL, WITH STANDART NON ASBESTOS NON METALLIC FILLER AND CARBON STEEL GUIDE RING, MATERIAL PER API STD 601 | 3" | und. | 4 | 272 | 10433 | TUVAPOR LTDA | 2015-10-30
| GASKET, SPIRAL WOUND , 1/8" THK, ANSI 600 AISI RF FLANGES, 304 SS WINDING MATERIAL, WITH STANDART NON ASBESTOS NON METALLIC FILLER AND CARBON STEEL GUIDE RING, MATERIAL PER API STD 601 | 12" | und. | 1 | 30 | FALTA REMISION | JD VALVULAS
| GASKET, SPIRAL WOUND , 1/8" THK, ANSI 600 AISI RF FLANGES, 304 SS WINDING MATERIAL, WITH STANDART NON ASBESTOS NON METALLIC FILLER AND CARBON STEEL GUIDE RING, MATERIAL PER API STD 601 | 2" | und. | 16 | 30 | FALTA REMISION | JD VALVULAS
| GASKET, SPIRAL WOUND , 1/8" THK, ANSI 600 AISI RF FLANGES, 304 SS WINDING MATERIAL, WITH STANDART NON ASBESTOS NON METALLIC FILLER AND CARBON STEEL GUIDE RING, MATERIAL PER API STD 601 | 2" | und. | 5 | 91 | RMC-1508583 | JD VALVULAS | 2015-08-27
| GASKET, SPIRAL WOUND , 1/8" THK, ANSI 600 AISI RF FLANGES, 304 SS WINDING MATERIAL, WITH STANDART NON ASBESTOS NON METALLIC FILLER AND CARBON STEEL GUIDE RING, MATERIAL PER API STD 601 | 2" | und. | 17 | 110 | RMC-1509588 | JD VALVULAS | 2015-09-11
| GASKET, SPIRAL WOUND , 1/8" THK, ANSI 600 AISI RF FLANGES, 304 SS WINDING MATERIAL, WITH STANDART NON ASBESTOS NON METALLIC FILLER AND CARBON STEEL GUIDE RING, MATERIAL PER API STD 601 | 10" | und. | 4 | 91 | RMC-1508583 | JD VALVULAS | 2015-08-27
| GASKET, SPIRAL WOUND , 1/8" THK, ANSI 600 AISI RF FLANGES, 304 SS WINDING MATERIAL, WITH STANDART NON ASBESTOS NON METALLIC FILLER AND CARBON STEEL GUIDE RING, MATERIAL PER API STD 601 | 10" | und. | 9 | 110 | RMC-1509588 | JD VALVULAS | 2015-09-11
| GASKET, SPIRAL WOUND , 1/8" THK, ANSI 600 AISI RF FLANGES, 304 SS WINDING MATERIAL, WITH STANDART NON ASBESTOS NON METALLIC FILLER AND CARBON STEEL GUIDE RING, MATERIAL PER API STD 601 | 10" | und. | 4 | 81 | RMC-1508579 | JD VALVULAS | 2015-08-26
| GASKET, SPIRAL WOUND , 1/8" THK, ANSI 600 AISI RF FLANGES, 304 SS WINDING MATERIAL, WITH STANDART NON ASBESTOS NON METALLIC FILLER AND CARBON STEEL GUIDE RING, MATERIAL PER API STD 601 | 16" | und. | 2 | 91 | RMC-1508583 | JD VALVULAS | 2015-08-27
| GASKET, SPIRAL WOUND , 1/8" THK, ANSI 600 AISI RF FLANGES, 304 SS WINDING MATERIAL, WITH STANDART NON ASBESTOS NON METALLIC FILLER AND CARBON STEEL GUIDE RING, MATERIAL PER API STD 601 | 3" | und. | 6 | 90 | RMC-1508582 | JD VALVULAS | 2015-08-27
| GASKET, SPIRAL WOUND , 1/8" THK, ANSI 600 AISI RF FLANGES, 304 SS WINDING MATERIAL, WITH STANDART NON ASBESTOS NON METALLIC FILLER AND CARBON STEEL GUIDE RING, MATERIAL PER API STD 601 | 4" | und. | 6 | 90 | RMC-1508582 | JD VALVULAS | 2015-08-27
| GASKET, SPIRAL WOUND , 1/8" THK, ANSI 600 AISI RF FLANGES, 304 SS WINDING MATERIAL, WITH STANDART NON ASBESTOS NON METALLIC FILLER AND CARBON STEEL GUIDE RING, MATERIAL PER API STD 601 | 4" | und. | 8 | 110 | RMC-1509588 | JD VALVULAS | 2015-09-11
| GASKET, SPIRAL WOUND , 1/8" THK, ANSI 600 AISI RF FLANGES, 304 SS WINDING MATERIAL, WITH STANDART NON ASBESTOS NON METALLIC FILLER AND CARBON STEEL GUIDE RING, MATERIAL PER API STD 601 | 6" | und. | 13 | 31 | 5112004740 | CASAVAL S.A | 2015-08-06
| GASKET, SPIRAL WOUND , 1/8" THK, ANSI 600 AISI RF FLANGES, 304 SS WINDING MATERIAL, WITH STANDART NON ASBESTOS NON METALLIC FILLER AND CARBON STEEL GUIDE RING, MATERIAL PER API STD 601 | 6" | und. | 8 | 84 | 5114019345 | CASAVAL S.A | 2015-08-27
| GASKET, SPIRAL WOUND , 1/8" THK, ANSI 600 AISI RF FLANGES, 304 SS WINDING MATERIAL, WITH STANDART NON ASBESTOS NON METALLIC FILLER AND CARBON STEEL GUIDE RING, MATERIAL PER API STD 601 | 6" | und. | 1 | 91 | RMC-1508583 | JD VALVULAS | 2015-08-27
| GASKET, SPIRAL WOUND , 1/8" THK, ANSI 600 AISI RF FLANGES, 304 SS WINDING MATERIAL, WITH STANDART NON ASBESTOS NON METALLIC FILLER AND CARBON STEEL GUIDE RING, MATERIAL PER API STD 601 | 8" | und. | 28 | 108 | S-001-00000010163 | TUVAPOR LTDA | 2015-09-02
| GASKET, SPIRAL WOUND , 1/8" THK, ANSI 600 AISI RF FLANGES, 304 SS WINDING MATERIAL, WITH STANDART NON ASBESTOS NON METALLIC FILLER AND CARBON STEEL GUIDE RING, MATERIAL PER API STD 601 | 8" | und. | 6 | 52 | 5112004774 | CASAVAL S.A | 2015-08-20
| GASKET, SPIRAL WOUND , 1/8" THK, ANSI 600 AISI RF FLANGES, 304 SS WINDING MATERIAL, WITH STANDART NON ASBESTOS NON METALLIC FILLER AND CARBON STEEL GUIDE RING, MATERIAL PER API STD 601 | 8" | und. | 33 | 31 | 5112004740 | CASAVAL S.A | 2015-08-06
| GASKET, SPIRAL WOUND , 1/8" THK, ANSI 600 AISI RF FLANGES, 304 SS WINDING MATERIAL, WITH STANDART NON ASBESTOS NON METALLIC FILLER AND CARBON STEEL GUIDE RING, MATERIAL PER API STD 601 | 8" | und. | 1 | 31 | 5112004740 | CASAVAL S.A | 2015-08-06
| GASKET, SPIRAL WOUND , 1/8" THK, ANSI 600 AISI RF FLANGES, 304 SS WINDING MATERIAL, WITH STANDART NON ASBESTOS NON METALLIC FILLER AND CARBON STEEL GUIDE RING, MATERIAL PER API STD 601 | 10" | und. | 14 | 30 | FALTA REMISION | JD VALVULAS
| GASKET, SPIRAL WOUND , 1/8" THK, ANSI 600 AISI RF FLANGES, 304 SS WINDING MATERIAL, WITH STANDART NON ASBESTOS NON METALLIC FILLER AND CARBON STEEL GUIDE RING, MATERIAL PER API STD 601 | 10" | und. | 1 | 127 | FALTA REMISION | JD VALVULAS
| GASKET, SPIRAL WOUND , 1/8" THK, ANSI 600 AISI RF FLANGES, 304 SS WINDING MATERIAL, WITH STANDART NON ASBESTOS NON METALLIC FILLER AND CARBON STEEL GUIDE RING, MATERIAL PER API STD 601 | 12" | und. | 1 | 168 | RMC-1509603 | JD VALVULAS | 2015-09-18
| GASKET, SPIRAL WOUND , 1/8" THK, ANSI 600 AISI RF FLANGES, 304 SS WINDING MATERIAL, WITH STANDART NON ASBESTOS NON METALLIC FILLER AND CARBON STEEL GUIDE RING, MATERIAL PER API STD 601 | 10" | und. | 13 | 168 | RMC-1509603 | JD VALVULAS | 2015-09-18
| GASKET, SPIRAL WOUND , 1/8" THK, ANSI 600 AISI RF FLANGES, 304 SS WINDING MATERIAL, WITH STANDART NON ASBESTOS NON METALLIC FILLER AND CARBON STEEL GUIDE RING, MATERIAL PER API STD 601 | 2" | und. | 32 | 168 | RMC-1509603 | JD VALVULAS | 2015-09-18
| GASKET, SPIRAL WOUND , 1/8" THK, ANSI 600 AISI RF FLANGES, 304 SS WINDING MATERIAL, WITH STANDART NON ASBESTOS NON METALLIC FILLER AND CARBON STEEL GUIDE RING, MATERIAL PER API STD 601 | 8" | und. | 5 | 91 | RMC-1508583 | JD VALVULAS | 2015-08-27
| GATE VALVE 1"X6000 THRD | 1" | und. | 1 | 204 |  | JD VALVULAS
| GATE VALVE 1"X800 | 1" | und. | 1 | 90 | RMC-1508582 | JD VALVULAS | 2015-08-27
| NIPPLE 1/2" X 4" S/160 | 1/2" | und. | 11 | 211 | 10381 | TUVAPOR | 2015-10-21
| NIPPLE 1 1/2" X 4" S/160 | 1 1/2" | und. | 8 | 211 | 10381 | TUVAPOR | 2015-10-21
| NIPPLE 1 1/2" X 8" S/160 PLANO/THRD | 1 1/2" | und. | 2 | 203 | 1510616 | JD VALVULAS | 2015-10-02
| NIPPLE 1" X 4" S/160 | 1" | und. | 33 | 211 | 10381 | TUVAPOR | 2015-10-21
| NIPPLE 1" X 4" S/80 | 1" | und. | 6 | 211 | 10381 | TUVAPOR | 2015-10-21
| NIPPLE 1" X 8" S/160 PLANO/THRD | 1" | und. | 15 | 203 | 1510616 | JD VALVULAS | 2015-10-02
| NIPPLE 3/4" X 4" S/160 | 3/4" | und. | 10 | 211 | 10381 | TUVAPOR | 2015-10-21
| NIPPLE 3/4" X 4" S/80 | 3/4" | und. | 7 | 211 | 10381 | TUVAPOR | 2015-10-21
| NIPPLE 4" X 100mm S/40 PLANO/THRD | 4" | und. | 2 | 272 | 10433 | TUVAPOR LTDA | 2015-10-30
| PIPE NIPPLE, 3/4"X4",S/80 1THRD | 3/4" | und. | 5 | 208 | RMC-1510623 | JD VALVULAS | 2015-10-14
| PIPE SMLS 1 1/2" SCH/160 THRD A53 GrB. GALVANIZED | 1 1/2" | mts | 6 | 30 | RMC-1508563 | JD VALVULAS | 2015-08-06
| PIPE SMLS 1" SCH/80 THRD A53 GrB. GALVANIZED | 1" | mts | 78 | 110 | RMC-1509588 | JD VALVULAS | 2015-09-11
| PIPE SMLS 1" SCH/80 THRD A53 GrB. GALVANIZED | 1" | mts | 36 | 30 | RMC-1508563 | JD VALVULAS | 2015-08-06
| PIPE SMLS, SCH/160, CS,BE, A 106 GR B, ASME B36.10. | 1/2" | mts | 6 | 209 | 10360 | TUVAPOR LTDA | 2015-10-15
| PIPE SMLS, SCH/160, CS,BE, A 106 GR B, ASME B36.10. | 1 1/2" | mts | 115 | 209 | 10360 | TUVAPOR LTDA | 2015-10-15
| PIPE SMLS, SCH/160, CS,BE, A 106 GR B, ASME B36.10. | 1" | mts | 204 | 209 | 10360 | TUVAPOR LTDA | 2015-10-15
| PIPE SMLS, SCH/160, CS,BE, A 106 GR B, ASME B36.10. | 1 1/2" | mts | 12 | 283 | 10451 | TUVAPOR LTDA | 2015-11-03
| PIPE SMLS, SCH/160, CS,PE, A 106 GR B, ASME B36.10. | 2" | mts | 60 | 31 | 5112004739 | CASAVAL S.A | 2015-08-06
| PIPE SMLS, SCH/160, CS,PE, A 106 GR B, ASME B36.10. | 2" | mts | 109.8 | 108 | S-001-00000010163 | TUVAPOR LTDA | 2015-09-02
| PIPE SMLS, SCH/40, CS, BE, A 106 GR B, ASME B36.10. | 4" | mts | 12.12 | 108 | S-001-00000010163 | TUVAPOR LTDA | 2015-09-02
| PIPE SMLS, SCH/40, CS, BE, A 106 GR B, ASME B36.10. | 4" | mts | 60 | CAMBIO | RMC-1509607 | JD VALVULAS | 2015-09-23
| PIPE SMLS, SCH/40, CS, BE, A 106 GR B, ASME B36.10. | 3" | mts | 127 | 283 | 10451 | TUVAPOR LTDA | 2015-11-03
| PIPE SMLS, SCH/40, CS, BE, A 106 GR B, ASME B36.10. | 3" | mts | 12 | 272 | 10433 | TUVAPOR LTDA | 2015-10-30
| PIPE SMLS, SCH/80, CS, BE, A 106 GR B, ASME B36.10. | 8" | mts | 24.24 | 204 | RMC-150619 | JD VALVULAS | 2015-10-05
| PIPE SMLS, SCH/80, CS, BE, A 106 GR B, ASME B36.10. | 1" | mts | 78 | 110 | RMC-1509588 | JD VALVULAS | 2015-09-11
| PIPE SMLS, SCH/80, CS, BE, A 106 GR B, ASME B36.10. | 1" | mts | 6 | 9O | RMC-1508582 | JD VALVULAS | 2015-08-27
| PIPE SMLS, SCH/80, CS, BE, A 106 GR B, ASME B36.10. | 10" | mts | 24.24 | 108 | S-001-00000010163 | TUVAPOR LTDA | 2015-09-02
| PIPE SMLS, SCH/80, CS, BE, A 106 GR B, ASME B36.10. | 10" | mts | 216 | 31 | 5112004739 | CASAVAL S.A | 2015-08-06
| PIPE SMLS, SCH/80, CS, BE, A 106 GR B, ASME B36.10. | 10" | mts | 6 | 84 | 5112004802 | CASAVAL S.A | 2015-08-27
| PIPE SMLS, SCH/80, CS, BE, A 106 GR B, ASME B36.10. | 2" | mts | 168 | 110 | RMC-1509588 | JD VALVULAS | 2015-09-11
| PIPE SMLS, SCH/80, CS, BE, A 106 GR B, ASME B36.10. | 3" | mts | 6 | 90 | RMC-1508582 | JD VALVULAS | 2015-08-27
| PIPE SMLS, SCH/80, CS, BE, A 106 GR B, ASME B36.10. | 4" | mts | 6 | 90 | RMC-1508582 | JD VALVULAS | 2015-08-27
| PIPE SMLS, SCH/80, CS, BE, A 106 GR B, ASME B36.10. | 4" | mts | 6 | 110 | RMC-1509588 | JD VALVULAS | 2015-09-11
| PIPE SMLS, SCH/80, CS, BE, A 106 GR B, ASME B36.10. | 4" | mts | 6 | 9O | RMC-1508582 | JD VALVULAS | 2015-08-27
| PIPE SMLS, SCH/80, CS, BE, A 106 GR B, ASME B36.10. | 6" | mts | 6 | 31 | 5112004739 | CASAVAL S.A | 2015-08-06
| PIPE SMLS, SCH/80, CS, BE, A 106 GR B, ASME B36.10. | 6" | mts | 12 | 31 | 5112004742 | CASAVAL S.A | 2015-08-06
| PIPE SMLS, SCH/80, CS, BE, A 106 GR B, ASME B36.10. | 6" | mts | 6 | 84 | 5112004802 | CASAVAL S.A | 2015-08-27
| PIPE SMLS, SCH/80, CS, BE, A 106 GR B, ASME B36.10. | 6" | mts | 24 | 132 | RMC-15091596 | JD VALVULAS | 2015-09-10
| PIPE SMLS, SCH/80, CS, BE, A 106 GR B, ASME B36.10. | 6" | mts | 6.06 | 108 | S-001-00000010163 | TUVAPOR LTDA | 2015-09-02
| PIPE SMLS, SCH/80, CS, BE, A 106 GR B, ASME B36.10. | 8" | mts | 36 | 52 | 5112004774 | CASAVAL S.A | 2015-08-20
| PIPE SMLS, SCH/80, CS, BE, A 106 GR B, ASME B36.10. | 8" | mts | 60 | 31 | 5112004742 | CASAVAL S.A | 2015-08-06
| PIPE SMLS, SCH/80, CS, BE, A 106 GR B, ASME B36.10. | 8" | mts | 6 | 84 | 5112004802 | CASAVAL S.A | 2015-08-27
| PIPE SMLS, SCH/80, CS, BE, A 106 GR B, ASME B36.10. | 2" | mts | 180 | 30 | FALTA REMISION | JD VALVULAS
| PIPE SMLS, SCH/80, CS, BE, A 106 GR B, ASME B36.10. | 2" | mts | 6.07 | 48 | FALTA REMISION | JD VALVULAS
| PIPE SMLS, SCH/80, CS, BE, A 106 GR B, ASME B36.10. | 2" | mts | 103.2 | 168 | RMC-1509603 | JD VALVULAS | 2015-09-18
| PIPE SMLS, SCH/80, CS, BE, A 106 GR B, ASME B36.10. | 10" | mts | 30 | 167 | S-001-0000010257 | TUVAPOR LTDA | 2015-09-18
| PIPE SMLS, SCH/80, CS, BE, A 106 GR B, ASME B36.10. | 8" | mts | 36.36 | 108 | S-001-00000010163 | TUVAPOR LTDA | 2015-09-02
| PIPE SMLS, SCH/80, CS, BE, A 106 GR B, ASME B36.10. | 8" | mts | 42 | 167 | S-001-0000010257 | TUVAPOR LTDA | 2015-09-18
| PIPE SMLS, SCH/80, CS, BE, A 106 GR B, ASME B36.10. | 2" | mts | 60.68 | 168 | RMC-150904 | JD VALVULAS | 2015-09-21
| PIPE SMLS, SCH/80, CS, BE, A 106 GR B, ASME B36.10. | 2" | mts | 149 | 283 | 10451 | TUVAPOR LTDA | 2015-11-03
| PIPE SMLS, SCH/80, CS, BE, A 106 GR B, ASME B36.10. | 1/2" | mts | 6 | 283 | 10451 | TUVAPOR LTDA | 2015-11-03
| PIPE SMLS, SCH/80, CS, BE, A 106 GR B, ASME B36.10. | 1" | mts | 212 | 283 | 10451 | TUVAPOR LTDA | 2015-11-03
| PIPE SMLS, SCH/80, CS, BE, A 106 GR B, ASME B36.10. | 1 1/2" | mts | 6 | 283 | 10451 | TUVAPOR LTDA | 2015-11-03
| PIPE SMLS, SCH/STD, CS, BE, A 106 GR B, ASME B36.10. | 8" | mts | 42 | 208 | RMC-1510622 | JD VALVULAS | 2015-10-13
| PIPE SMLS, SCH/STD, CS, BE, A 106 GR B, ASME B36.10. | 8" | und. | 6 | 137 | FALTA REMISION | JD VALVULAS | 2015-09-11
| PIPE SMLS, SCH/STD, CS, BE, A 106 GR B, ASME B36.10. | 8" | mts | 12 | 167 | S-001-0000010257 | TUVAPOR LTDA | 2015-09-18
| PIPE SMLS, SCH/STD, CS, BE, A 106 GR B, ASME B36.10. | 8" | mts | 6 | 283 | 10451 | TUVAPOR LTDA | 2015-11-03
| PIPE SMLS, SCH/STD, CS,BE, A 106 GR B, ASME B36.10. | 16" | mts | 60 | 31 | 5112004742 | CASAVAL S.A | 2015-08-06
| PIPE SMLS, SCH/STD, CS,BE, A 106 GR B, ASME B36.10. | 16" | mts | 180 | 31 | 5112004741 | CASAVAL S.A | 2015-08-06
| PIPE SMLS, SCH/STD, CS,BE, A 106 GR B, ASME B36.10. | 6" | mts | 18 | 31 | 5112004739 | CASAVAL S.A | 2015-08-06
| PIPE SMLS, SCH/STD, CS,BE, A 106 GR B, ASME B36.10. | 6" | mts | 6.06 | 108 | S-001-00000010163 | TUVAPOR LTDA | 2015-09-02
| PIPE SMLS, SCH/STD, CS,BE, A 106 GR B, ASME B36.10. | 6" | mts | 6 | 157 | RMC-1509602 | JD VALVULAS | 2015-09-16
| PIPE SMLS, SCH/STD, CS,BE, A 106 GR B, ASME B36.10. | 6" | mts | 12 | 168 | RMC-1509603 | JD VALVULAS | 2015-09-18
| PIPE SMLS, SCH/STD, CS,BE, A 106 GR B, ASME B36.10. | 16" | mts | 12 | 210 | 5112004962 | CASAVAL S.A | 2015-10-16
| PLUG CC, CLASS 3000, ASTM A105 ROUND HEAD, THRD 1" | 1" | und. | 1 | 209 | 10360 | TUVAPOR LTDA | 2015-10-15
| PLUG CC, CLASS 3000, ASTM A105 ROUND HEAD, THRD 1/2" | 1/2" | und. | 5 | 209 | 10360 | TUVAPOR LTDA | 2015-10-15
| PLUG CC, CLASS 3000, ASTM A105 ROUND HEAD, THRD 3/4" | 3/4" | und. | 8 | 209 | 10360 | TUVAPOR LTDA | 2015-10-15
| PLUG CC, CLASS 6000, ASTM A105 ROUND HEAD, THRD 1" | 1" | und. | 1 | 209 | 10360 | TUVAPOR LTDA | 2015-10-15
| PLUG CC, CLASS 6000, ASTM A105 ROUND HEAD, THRD 1/2" | 1/2" | und. | 6 | 209 | 10360 | TUVAPOR LTDA | 2015-10-15
| PLUG CC, CLASS 6000, ASTM A105 ROUND HEAD, THRD 3/4" | 3/4" | und. | 4 | 209 | 10360 | TUVAPOR LTDA | 2015-10-15
| PLUG ROUND 1/2" 3-6000LB A105N | 1/2" | und. | 3 | 108 | S-001-00000010163 | TUVAPOR LTDA | 2015-09-02
| REDUCER, CONC S/160,ASTM A-234 GR WPB,ASME B16.9. | 4"X2" | und. | 1 | 209 | 10360 | TUVAPOR LTDA | 2015-10-15
| REDUCER, CONC S/160,ASTM A-234 GR WPB,ASME B16.9. | 12"X8" | und. | 2 | 45 | FALTA REMISION
| REDUCER, CONC S/160,ASTM A-234 GR WPB,ASME B16.9. | 2"x1 1/2" | und. | 3 | 209 | 10366 | TUVAPOR LTDA | 2015-10-16
| REDUCER, CONC S/160,ASTM A-234 GR WPB,ASME B16.9. | 2"x1" | und. | 5 | 209 | 10366 | TUVAPOR LTDA | 2015-10-16
| REDUCER, CONC S/80,ASTM A-234 GR WPB,ASME B16.9. | 4"X2" | und. | 6 | 206 | RMC-1510621 | JD VALVULAS | 2015-10-06
| REDUCER, CONC S/80,ASTM A-234 GR WPB,ASME B16.9. | 4"X2" | und. | 2 | 209 | 10360 | TUVAPOR LTDA | 2015-10-15
| REDUCER, CONC S/80,ASTM A-234 GR WPB,ASME B16.9. | 10"X6" | und. | 2 | 108 | S-001-00000010163 | TUVAPOR LTDA | 2015-09-02
| REDUCER, CONC S/80,ASTM A-234 GR WPB,ASME B16.9. | 10"X8" | und. | 3 | 110 | RMC-1509588 | JD VALVULAS | 2015-09-11
| REDUCER, CONC S/80,ASTM A-234 GR WPB,ASME B16.9. | 10"X8" | und. | 1 | 30 | FALTA REMISION | JD VALVULAS
| REDUCER, CONC S/80,ASTM A-234 GR WPB,ASME B16.9. | 4"X2" | und. | 3 | 209 | 10366 | TUVAPOR LTDA | 2015-10-16
| REDUCER, CONC S/STD,ASTM A-234 GR WPB,ASME B16.9. | 8"X6" | und. | 5 | 208 | RMC-1510623 | JD VALVULAS | 2015-10-14
| REDUCER, CONC S/STD,ASTM A-234 GR WPB,ASME B16.9. | 4"X2" | und. | 1 | 209 | 10360 | TUVAPOR LTDA | 2015-10-15
| REDUCER, CONC S/STD,ASTM A-234 GR WPB,ASME B16.9. | 8"X4" | und. | 7 | 168 | RMC-1509603 | JD VALVULAS | 2015-09-18
| REDUCER, CONC S/STD,ASTM A-234 GR WPB,ASME B16.9. | 4"X3" | und. | 2 | 272 | 10433 | TUVAPOR LTDA | 2015-10-30
| SOCKOLET, 3000LB,CS,ASTM A-105,MSS SP-97, SW-BW, ASME B16.11. | 1" | und. | 9 | 209 | 10360 | TUVAPOR LTDA | 2015-10-15
| SOCKOLET, 3000LB,CS,ASTM A-105,MSS SP-97, SW-BW, ASME B16.11. | 1" | und. | 3 | 30 | RMC-1508563 | JD VALVULAS | 2015-08-06
| SOCKOLET, 3000LB,CS,ASTM A-105,MSS SP-97, SW-BW, ASME B16.11. | 3/4" | und. | 1 | 156 | S-001-00000010251 | TUVAPOR LTDA | 2015-09-17
| SOCKOLET, 3000LB,CS,ASTM A-105,MSS SP-97, SW-BW, ASME B16.11. | 1" | und. | 7 | 168 | RMC-1509603 | JD VALVULAS | 2015-09-18
| SOCKOLET, 3000LB,CS,ASTM A-105,MSS SP-97, SW-BW, ASME B16.11. | 3/4" | und. | 9 | 167 | S-001-0000010257 | TUVAPOR LTDA | 2015-09-18
| SOCKOLET, 3000LB,CS,ASTM A-105,MSS SP-97, SW-BW, ASME B16.11. | 1/2" | und. | 10 | 167 | S-001-0000010257 | TUVAPOR LTDA | 2015-09-18
| SOCKOLET, 3000LB,CS,ASTM A-105,MSS SP-97, SW-BW, ASME B16.11. | 3/4" | und. | 1 | 211 | 10366 | TUVAPOR LTDA | 2015-10-16
| SOCKOLET, 6000LB,CS,ASTM A-105,MSS SP-97, SW-BW, ASME B16.11. | 1 1/2" | und. | 2 | 203 | 1510616 | JD VALVULAS | 2015-10-02
| SOCKOLET, 6000LB,CS,ASTM A-105,MSS SP-97, SW-BW, ASME B16.11. | 3/4" | und. | 5 | 208 | RMC-1510622 | JD VALVULAS | 2015-10-13
| SOCKOLET, 6000LB,CS,ASTM A-105,MSS SP-97, SW-BW, ASME B16.11. | 1/2" | und. | 2 | 208 | RMC-1510623 | JD VALVULAS | 2015-10-14
| SOCKOLET, 6000LB,CS,ASTM A-105,MSS SP-97, SW-BW, ASME B16.11. | 1" | und. | 1 | 108 | S-001-00000010163 | TUVAPOR LTDA | 2015-09-02
| SOCKOLET, 6000LB,CS,ASTM A-105,MSS SP-97, SW-BW, ASME B16.11. | 1/2" | und. | 5 | 108 | S-001-00000010163 | TUVAPOR LTDA | 2015-09-02
| SOCKOLET, 6000LB,CS,ASTM A-105,MSS SP-97, SW-BW, ASME B16.11. | 1" | und. | 3 | 110 | RMC-1509588 | JD VALVULAS | 2015-09-11
| SOCKOLET, 6000LB,CS,ASTM A-105,MSS SP-97, SW-BW, ASME B16.11. | 1" | und. | 3 | 30 | RMC-1508563 | JD VALVULAS | 2015-08-06
| SOCKOLET, 6000LB,CS,ASTM A-105,MSS SP-97, SW-BW, ASME B16.11. | 2" | und. | 1 | 108 | S-001-00000010163 | TUVAPOR LTDA | 2015-09-02
| SOCKOLET, 6000LB,CS,ASTM A-105,MSS SP-97, SW-BW, ASME B16.11. | 3/4" | und. | 2 | 108 | S-001-00000010163 | TUVAPOR LTDA | 2015-09-02
| SOCKOLET, 6000LB,CS,ASTM A-105,MSS SP-97, SW-BW, ASME B16.11. | 1" | und. | 2 | 167 | S-001-0000010257 | TUVAPOR LTDA | 2015-09-18
| SOCKOLET, 6000LB,CS,ASTM A-105,MSS SP-97, SW-BW, ASME B16.11. | 3/4" | und. | 5 | 167 | S-001-0000010257 | TUVAPOR LTDA | 2015-09-18
| SOCKOLET, 6000LB,CS,ASTM A-105,MSS SP-97, SW-BW, ASME B16.11. | 2" | und. | 1 | 204 |  | JD VALVULAS
| SOCKOLET, 6000LB,CS,ASTM A-105,MSS SP-97, SW-BW, ASME B16.11. | 1/2" | und. | 3 | 211 | 10366 | TUVAPOR LTDA | 2015-10-16
| SOCKOLET, 6000LB,CS,ASTM A-105,MSS SP-97, SW-BW, ASME B16.11. | 3/4" | und. | 1 | 211 | 10366 | TUVAPOR LTDA | 2015-10-16
| STUDS BOLDS 1 1/4"X7 1/2" 2H A 194 | 1 1/4"X7 1/2" | und. | 64 | 91 | RMC-1508583 | JD VALVULAS | 2015-08-27
| STUDS BOLDS 1 1/8"X15" 2H A 194 | 1 1/8"X15" | und. | 24 | 110 | RMC-1509588 | JD VALVULAS | 2015-09-11
| STUDS BOLDS 1 1/8"X7 1/2" 2H A 194 | 1 1/8"X7 1/2" | und. | 60 | 91 | RMC-1508583 | JD VALVULAS | 2015-08-27
| STUDS BOLDS 1 1/8X7 1/2" W/2HVY HEX NUTS A 194 | 1 1/8X7 1/2" | und. | 24 | 53 | RMC-1508572 | JD VALVULAS | 2015-08-18
| STUDS BOLDS 1"X5 1/2" 2H A 194 | 1"X5 1/2" | und. | 32 | 91 | RMC-1508583 | JD VALVULAS | 2015-08-27
| STUDS BOLDS 1"X5 1/2" 2H A 194 | 1"X5 1/2" | und. | 80 | 110 | RMC-1509588 | JD VALVULAS | 2015-09-11
| STUDS BOLDS 1"X6 1/2" 2H A 194 | 1"X6 1/2" | und. | 12 | 91 | RMC-1508583 | JD VALVULAS | 2015-08-27
| STUDS BOLDS 3/4"X4" 2H A 194 | 3/4"X4 | und. | 48 | 91 | RMC-1508583 | JD VALVULAS | 2015-08-27
| STUDS BOLDS 3/4"X4" 2H A 194 | 3/4"X4" | und. | 8 | 91 | RMC-1508583 | JD VALVULAS | 2015-08-27
| STUDS BOLDS 5/8"X3 3/4" 2H A 193 GR.B7 | 5/8"X3 3/4" | und. | 2 | 272 | 10433 | TUVAPOR LTDA | 2015-10-30
| STUDS BOLDS 5/8"X4 1/2" 2H A 194 | 5/8"X4 1/2" | und. | 40 | 91 | RMC-1508583 | JD VALVULAS | 2015-08-27
| STUDS BOLDS 7/8"X6" 2H A 194 | 7/8"X6" | und. | 48 | 9O | RMC-1508582 | JD VALVULAS | 2015-08-27
| STUDS BOLDS 7/8"X6" 2H A 194 | 7/8"X6" | und. | 32 | 110 | RMC-1509588 | JD VALVULAS | 2015-09-11
| STUDS BOLDS 7/8"X6" W/2HVY HEX NUTS A 194 | 7/8"X6" | und. | 48 | 90 | RMC-1508582 | JD VALVULAS | 2015-08-27
| SWAGE CONCENTRIC SCH 80 A 106 THR 2"X1 1/2" | 2"X1 1/2" | und. | 1 | 168 | RMC-150904 | JD VALVULAS | 2015-09-21
| SWAGE CONCENTRIC SCH 80 A 106 THR 2"X1" | 2"X1" | und. | 1 | 168 | RMC-150904 | JD VALVULAS | 2015-09-21
| SWAGE CONCENTRIC SCH 80 A 106 THR 2X1" | 2X1" | und. | 1 | 108 | S-001-00000010188 | TUVAPOR LTDA | 2015-09-07
| TEE, REDUCING 1 1/2"x3/4" 6000Lb THRD ASTM A 105 | 1 1/2"x3/4" | und. | 2 | 209 | 10360 | TUVAPOR LTDA | 2015-10-15
| TEE, REDUCING S/80, ASTM A-234 GR WPB,ASME B16.9. | 2"X1" | und. | 2 | 209 | 10360 | TUVAPOR LTDA | 2015-10-15
| TEE, REDUCING S/80, ASTM A-234 GR WPB,ASME B16.9. | 10"X6" | und. | 3 | 30 | FALTA REMISION | JD VALVULAS
| TEE, REDUCING S/80, ASTM A-234 GR WPB,ASME B16.9. | 10"X8" | und. | 9 | 30 | RMC-1508563 | JD VALVULAS | 2015-08-06
| TEE, REDUCING S/80, ASTM A-234 GR WPB,ASME B16.9. | 10"X4" | und. | 3 | 83 | 1048 | PETROEXA LTDA | 2015-09-02
| TEE, REDUCING S/80, ASTM A-234 GR WPB,ASME B16.9. | 10"x4" | und. | 3 | 90 | RMC-1508582 | JD VALVULAS | 2015-08-27
| TEE, REDUCING S/80, ASTM A-234 GR WPB,ASME B16.9. | 10"X6" | und. | 3 | 81 | RMC-1508579 | JD VALVULAS | 2015-08-26
| TEE, REDUCING S/80, ASTM A-234 GR WPB,ASME B16.9. | 10"X6" | und. | 2 | 110 | RMC-1509588 | JD VALVULAS | 2015-09-11
| TEE, REDUCING S/80, ASTM A-234 GR WPB,ASME B16.9. | 10"X8" | und. | 1 | 81 | RMC-1508579 | JD VALVULAS | 2015-08-26
| TEE, REDUCING S/80, ASTM A-234 GR WPB,ASME B16.9. | 4"X2" | und. | 5 | 108 | S-001-00000010163 | TUVAPOR LTDA | 2015-09-02
| TEE, REDUCING S/80, ASTM A-234 GR WPB,ASME B16.9. | 8"x6" | und. | 3 | 53 | RMC-1508572 | JD VALVULAS | 2015-08-18
| TEE, REDUCING S/STD, ASTM A-234 GR WPB,ASME B16.9. | 4"X2" | und. | 7 | 157 | RMC-1509601 | JD VALVULAS | 2015-09-18
| TEE, REDUCING S/STD, ASTM A-234 GR WPB,ASME B16.9. | 4"X2" | und. | 2 | 199 | RMC-1509611 | JD VALVULAS | 2015-09-29
| TEE, REDUCING S/STD, ASTM A-234 GR WPB,ASME B16.9. | 3"x2" | und. | 1 | 272 | 10433 | TUVAPOR LTDA | 2015-10-30
| TEE, STR 1 1/2" 6000Lb THRD ASTM A 105 | 1 1/2" | und. | 2 | 30 | RMC-1508563 | JD VALVULAS | 2015-08-06
| TEE, STR 1 1/2" 6000Lb THRD ASTM A 105 | 1 1/2" | und. | 49 | 214 | 1510625 | JD VALVULAS | 2015-10-16
| TEE, STR 1" 3000Lb SCH 160 THR A105 GALVANIZED | 1" | und. | 2 | 110 | RMC-1509588 | JD VALVULAS | 2015-09-11
| TEE, STR 1" 3000Lb SW A105 | 1" | und. | 6 | 209 | 10366 | TUVAPOR LTDA | 2015-10-16
| TEE, STR 1" 3000Lb THR A105 | 1" | und. | 1 | 108 | S-001-00000010163 | TUVAPOR LTDA | 2015-09-02
| TEE, STR. S/160, ASTM A-234 GR WPB,ASME B16.9. | 2" | und. | 2 | 209 | 10360 | TUVAPOR LTDA | 2015-10-15
| TEE, STR. S/80, ASTM A-234 GR WPB,ASME B16.9. | 2" | und. | 6 | 137 | FALTA REMISION | JD VALVULAS | 2015-09-11
| TEE, STR. S/80, ASTM A-234 GR WPB,ASME B16.9. | 2" | und. | 3 | 110 | RMC-1509588 | JD VALVULAS | 2015-09-11
| TEE, STR. S/80, ASTM A-234 GR WPB,ASME B16.9. | 6" | und. | 1 | 30 | RMC-1508563 | JD VALVULAS | 2015-08-06
| TEE, STR. S/80, ASTM A-234 GR WPB,ASME B16.9. | 8" | und. | 1 | 53 | RMC-1508572 | JD VALVULAS | 2015-08-18
| TEE, STR. S/80, ASTM A-234 GR WPB,ASME B16.9. | 8" | und. | 7 | 30 | RMC-1508563 | JD VALVULAS | 2015-08-06
| TEE, STR. S/80, ASTM A-234 GR WPB,ASME B16.9. | 8" | und. | 5 | 30 | FALTA REMISION | JD VALVULAS
| TEE, STR. S/80, ASTM A-234 GR WPB,ASME B16.9. | 8" | und. | 3 | 168 | RMC-1509603 | JD VALVULAS | 2015-09-18
| TEE, STR. S/80, ASTM A-234 GR WPB,ASME B16.9. | 2" | und. | 9 | 30 | RMC-1508563 | JD VALVULAS | 2015-08-06
| THREADOLET, 3000Lb A105N GLAVANIZED | 1" | und. | 1 | 108 | S-001-00000010172 | TUVAPOR LTDA | 2015-09-02
| THREADOLET, 3000Lb A105N GLAVANIZED | 1" | und. | 2 | 209 | 10366 | TUVAPOR LTDA | 2015-10-16
| THREADOLET,3000Lb A105N GLAVANIZED | 1" | und. | 1 | 9O | RMC-1508582 | JD VALVULAS | 2015-08-27
| THREDOLET,3000LB, CS,ASTM A-105,MSS SP-97, THRD-BW, ASME B16.11. | 1" | und. | 2 | 199 | RMC-1509611 | JD VALVULAS | 2015-09-29
| THREDOLET,3000LB, CS,ASTM A-105,MSS SP-97, THRD-BW, ASME B16.11. | 1" | und. | 2 | 272 | 10433 | TUVAPOR LTDA | 2015-10-30
| THREDOLET,6000LB, CS,ASTM A-105,MSS SP-97, THRD-BW, ASME B16.11. | 1" | und. | 1 | 108 | S-001-00000010163 | TUVAPOR LTDA | 2015-09-02
| UNION, THRD 6000LB,ASTM A105 1 1/2" | 1 1/2" | und. | 2 | 209 | 10360 | TUVAPOR LTDA | 2015-10-15
| UNION, THRD 6000LB,ASTM A105 1 1/2" | 1" | und. | 4 | 209 | 10360 | TUVAPOR LTDA | 2015-10-15
| UNIVERSAL UNION 1" SW 3000 | 1" | und. | 8 | 31 | 5114019101 | CASAVAL S.A | 2015-08-06
| WELDOLET,BW,S/160,CS,ASTM A-105, MSS-SP-97,ASME B16.25. | 2" | und. | 2 | 209 | 10366 | TUVAPOR LTDA | 2015-10-16
| WELDOLET,BW,S/80,CS,ASTM A-105, MSS-SP-97,ASME B16.25. | 2" | und. | 1 | 110 | RMC-1509588 | JD VALVULAS | 2015-09-11
| WELDOLET,BW,S/80,CS,ASTM A-105, MSS-SP-97,ASME B16.25. | 3" | und. | 3 | 132 | RMC-15091596 | JD VALVULAS | 2015-09-10
| WELDOLET,BW,S/80,CS,ASTM A-105, MSS-SP-97,ASME B16.25. | 2" | und. | 1 | 30 | RMC-1508563 | JD VALVULAS | 2015-08-06
| WELDOLET,BW,S/80,CS,ASTM A-105, MSS-SP-97,ASME B16.25. | 2" | und. | 6 | 137 | FALTA REMISION | JD VALVULAS | 2015-09-11
| WELDOLET,BW,S/80,CS,ASTM A-105, MSS-SP-97,ASME B16.25. | 2" | und. | 17 | 168 | RMC-1509603 | JD VALVULAS | 2015-09-18
| PIPE SMLS, SCH/STD, CS,BE, A 106 GR B, ASME B36.10. | 16" | mts | 96 | 282 | 5112004999 | CASAVAL S.A | 2015-11-04